2010 - 2015 Airport Capital Improvement Plan 

Airport: Nevada County Airport









Date: January 15, 2010

Associated City: Grass Valley









NPIAS Number:
State: CA

	Project  

Number
	Funding 

Year
	Project Description
	Federal
	CA State match
	Local
	Total Cost

	Complete
	2006
	Ramp II Reconstruction  (Phase II construction)
	$  617,500
	$ 15,437
	$ 17,062
	$  650,000 (compl)

	Complete
	2006
	Prelim design (30%) and environmental baseline on RSA  (P I)
	$    47,500
	$   1188
	$   1312
	$    50,000 (compl)

	FAA review
	2007
	Airport Layout Plan Update
	$    75,000
	$   1875
	$    2072
	$    78,947(in work)

	In Work
	2008
	Final design and construction est. for RSA improvement  (P II)
	$  142,500
	$   3563
	$   3937
	$  150,000(in work)

	In Work
	2008
	Develop pavement maintenance plan
	$      9,500
	$     238
	$     262
	$    10,000(in work) 

	In Work
	2009
	EA for land acquisitions, perimeter fence upgrade & clearing
	$   142,500
	0
	$   7,500
	$   150,000

	1
	2010
	Engineering for Runway 07/25 asphalt repair 
	$     80,750
	0
	$   4,250
	$     85,000

	2
	2011
	RSA Improvement Construction (P III)
	$1,472,500
	0
	$ 77,500
	$1,550,000

	3
	
	RWY 07/25 Repair
	$   774,250
	0
	$ 40,750
	$   815,000

	4
	2012
	Land acquisition for airport expansion 
	$1,425,000
	0
	$ 75,000
	$1,500,000

	5
	2013
	Upgrade/Repair perimeter fencing (Phase I design & engr)
	$     95,000
	0
	$    5,000
	$   100,000

	6
	
	Obstruction removal in ~ 20 acres east of airport
	$     95,000
	0
	$    5,000 
	$   100,000

	7
	2014
	Upgrade/Repair perimeter fencing  (Phase II construction)
	$   427,500
	0
	$  20,500 
	$   450,000

	8
	2015
	Land Acquisition for Ramp 5 expansion & RPZ protection
	$1,900,000
	0
	$100,000
	$2,000,000
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Airport Capital Improvement Program

Nevada County Airport

Nevada County, California

Program Narrative

Project No. 1 – Engineering to develop asphalt repairs on Runway 07/25 
Longitudinal cracks along pavement seams in the landing areas on Runway 07/25 have reached a point where rehabilitation is necessary.  This project will be the engineering and construction cost estimate phase of the rehabilitation.  The deliverable from this project will be used as the basis for a competitive bid to do the runway repairs/rehabilitation.   

Project No. 2 – (Phase III) RSA Improvement Construction phase and RWY 7/25 Rehabilitation 

This is the third or construction phase of RSA drainage and erosion improvement project.  When the final engineering study funded in 2008 is complete this phase can be more accurately described and cost reflected.

Project No. 3 – Runway 7/25 Repair and Rehabilitation

The Runway 7/25 west area needs to be reconstructed by milling off the entire AC layer and replacing it with 4" of new HMA.  This will in part also help to correct the drainage issues in this area.  The Runway 7/25 Center and East areas shall receive a slurry seal after the existing cracks have been cleaned and sealed.

Project No. 4. – Land Acquisition for Airport Expansion

Two sites potentially offer the opportunity for the airport to acquire additional property to support airport expansion, build ramps & hangars, support additional FBOs and CDF expansion plans.  First is private property adjacent to the current USFS/CDF compound and the second is private property currently zoned industrial on the north side of the airport from mid-field to the western boundary.  The more likely of the two is the 47 acres on the north side currently zoned M-1 (Light Industrial).    

Project No. 5 – (Phase I) Perimeter Fencing Design and Engineering & Obstruction Removal 

Fencing along portions of the airport perimeter is not adequate for keeping people or deer from accessing the runway. Additionally all three vehicle access gates require upgrading.  This project is the preliminary design review and engineering requirements for update of perimeter fencing and access gates.

Project No. 6 – Obstruction Removal
The second of two FY 2013 projects is obstruction removal on the ~ 20 acres to the east of the airport on the approach to Runway 25.  This obstruction removal is necessary to maintain 20 to 1 clearances in this zone.  

Project No 7. – (Phase II) Perimeter Fencing.

This project is the construction phase of the perimeter fencing and access gate upgrade.  

Project No 8. – Acquire DOT’s portion of Lot Six (4.13Acres)

The Nevada County Department of Transportation and Sanitation currently owns the southern 4.13 acres of lot Six. Two buildings exist on this site, a 4000 sq. ft. Office building and a maintenance building of about 6000 sq. ft. The acquisition would include both buildings and land that would be used for airport purposes. 

Additional land in the vicinity of Lot 6 also needs to be evaluated for potential acquisition.  The Waste Management and Amerigas sites off Grass Valley Avenue are in such proximity to the airport as to be considered safety hazards (inside the RPZ).  Acquisition of these sites could alleviate the safety issue and redevelopment of the sites with low risk enterprises could provide revenue to the airport.

