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   MOAB AREA TRAVEL COUNCIL

REQUEST FOR PROPOSAL

ACTIVITIES GUIDE

The Moab Area Travel Council is the Destination Marketing Organization for Grand County, Utah.  The office is located in downtown Moab, and is a branch of the County Government.  The mission of the Travel Council is market the area to potential visitors to increase the number of visitors coming to Grand County each year.  We accomplish this through the fine collateral we have as well as our web and social presence. 
PURPOSE:  To select a Company or Person, that will work with a Travel Council Staff member through completion, to design and layout a new, full/color travel guide.
ACTIVITIES GUIDE DESCRIPTION:
 

# of pages To be determined -  Current Guide is 36 pages and can be viewed at www.discovermoab.com
 6 ¼ “w X 10”h - finished size (will discuss with designer)

 Cover is portrait orientation 6 ¼” w X 10” h, interior pages will be landscape orientation 10”w X 6 ¼” h
 60 # paper inside with heavier cover (designer to recommend stock)
 75% photo and text, 25% charts

4 color two sides throughout with bleeds

PHOTOS: the Travel Council will provide photos, and all photos used will include a credit to the photographer.

TEXT:  Designer will work with the Travel Council Staff that will provide text and degree of content.  The Travel Council will appoint one person from within its staff to serve as a project coordinator.  The Travel Council will provide appropriate support documentation for the successful completion of the project.  
SCHEDULE: 
· Proposals due by Oct. 30, 2009

· Project awarded November 18, 2009 
· Design and guidelines for textual/chart content must be determined by December 1st, 

· 2009

· The textual/chart content will be created by the Travel Council staff and will not be completely available until early January, 2010

· Final edits and final approval must be completed by February 26, 2010

· Disc/Files ready for printer by Feb. 26, 2010

Electronic proofs will be used to monitor the design process and will be presented to the Marketing Committee of the Moab Area Travel Council for approval.

OWNERSHIP:  At the conclusion of the project all materials developed by the designer on this Activities Planner will be the exclusive property of the Moab Area Travel Council.

PROPOSAL INCLUSIONS: 
Proposal must include a technical section and a time-cost section.   The technical section should include timelines, number of persons necessary to complete the project and schedules for completing the project.  The time-cost section should detail the time and cost breakdown necessary to complete the job.   Bidders must include a portfolio of work that they have personally designed or overseen that will not be returned to them unless return Fed-X or UPS prepaid forms are included.  Proposals submitted without samples will not be considered. 
References may be requested after proposals have been received. 

PROPOSAL DEADLINE:  October 30, 2009, 5PM. NO faxed or electronic proposals will be accepted.

PROPOSAL SUBMISSION:  Submit proposals to:
Marian DeLay

Moab Area Travel Council

P.O. Box 550

84 North 100 East
Moab, Utah  84532

Phone: 435-259-1370

Fax: 435-259-1376

mdelay@discovermoab.com
For additional information contact:  Marian DeLay at the above contact location. 

Proposals may be rated on a combination of qualifiers, such as:

Dollar amount

Presentation 

Sample work

References

